## Agenda
Sprint Planning Meeting 2 |  |  |  | Notes:
Group Number: | 1 |  |  | Replace ## actual sprint planning number and group number respectively.
This spreadsheet contains more than one sheet; after you are done with Attendees information, complete information on sheet "Current Sprint"
Attendees (Last name, First Name) | Present | Absent | Notes/Comments | Complexity and number of items must be reasonable according to the number of team members.
Bechera Chapman-Tremblay | X |  |  | Your professor might ask you to add more user stories and or increase complexity/functionality.
Gerald Prowse | X |  |  | "Current Sprint" information will be used as a checklist to grade your sprint release.
Hunter Mcneil | X
Viktor Avelino Araujo | X
Ahmad Al-Sarraf | X
Add a screenshot of your "Agile Task Board" below:

## Current Sprint
Sprint 02 | 1 |  |  |  | Group Number: | 1 |  | Notes:
Feel free to replace below table with your CSV export, make sure to format table as needed in order to support column filtering | [7 empty] | Bring information from your product backlog to identify "user stories" that will become part of your current sprint release. You can copy paste or replace table entirely using your CSV export. You can as change column names to match your format as needed.
Task ID | As a (short text) | I want to | So I Can (short text) | Assignee | Notes | Priority | Status
15 | User | Change profile picture | So other members know who I am | Bechera Chapman-Tremblay |  | 1 | Done
16 | User | Change my email | Remove old email addresses I no longer use | Bechera Chapman-Tremblay |  | 1 | Done
17 | User | Change my name | Change any incorrect info | Hunter McNeil |  | 1 | Done
25 | User | Create a new budget | Add a new budget to my account | Hunter McNeil |  | 1 | Done
27 | User | Delete budgets | remove budgets that are linked to my account | Ahmad Al-Sarraf |  | 1 | Done
35 | User | Set name of budget | Customize titles of budgets | Hunter McNeil |  | 1 | Done
36 | User | Select a date for an expense | Add a date dd-mm-yy format to add more info for an expense | Bechera Chapman-Tremblay |  | 1 | Done
29 | User | Edit a budget | cusomize budgets | Ahmad Al-Sarraf |  | 1 | Done
37 | User | Set expense as paid/unpaid | Know that the expense is either paid or not | Viktor Avelino Araujo |  | 1 | Done
38 | User | Set a description for an expense | add more information to the expense | Hunter McNeil |  | 1 | Done
39 | User | See all expenses that belong to a budget | Get a sense of how all budgets are doing | Gerald Prowse |  | 1 | Done
40 | User | Set a name for an expense | Customize title of expense | Gerald Prowse |  | 1 | Done
42 | User | Set an amount for an expense | Set a limit | Ahmad Al-Sarraf |  | 1 | Done
44 | User | Delete an expense | remove irrelevant or incorrect expenses | Gerald Prowse |  | 1 | Done
47 | User | Create an expense | Link expenses to my profile | Ahmad Al-Sarraf |  | 1 | Done
48 | User | Edit an expense | Customize my expenses | Bechera Chapman-Tremblay |  | 1 | Done

## Technology
Questions: | Answers
Front End Technology? | Vite (React), Typescript, Tailwind CSS, SCSS/SASS
Are you using or plan to use a Data Base? | Yes
If Yes which DB engine are you using? | Firebase
Which application server are you using? | Firebase
Describe here any additional technologies | OAuth w/firebase
Additional Notes